## Application Inventory
Application Inventory
List of IT applications/platform services being assessed.
Application ID | Application ID | Type | Business Unit | Criticality | Hosting | Technology | Owner Role | Status
APP-001 | Finance ERP | Application | Finance | Business Critical | Cloud | SAP S/4HANA | Owner - Finance IT | Active
APP-002 | HR Portal | Application | HR | High | Cloud | Workday | Owner - HR IT | Active
APP-003 | Customer API Gateway | Platform Service | Digital | Business Critical | Cloud | API Management | Platform Team | Active
APP-004 | Manufacturing MES | Application | Operations | Business Critical | On-Prem | MES Platform | OT Applications | Active
APP-005 | Supplier Portal | Application | Procurement | High | Cloud | Web Application | Procurement IT | Active
APP-006 | Data Lake Platform | Platform Service | Data & Analytics | High | Cloud | Azure Data Lake | Data Platform | Active
APP-007 | Identity Service | Platform Service | Enterprise IT | Business Critical | Hybrid | Entra ID / AD | IAM Team | Active
APP-008 | ITSM Platform | Application | IT | High | Cloud | ServiceNow | IT Operations | Active
APP-009 | Corporate Collaboration | Application | Corporate | Medium | Cloud | M365 | Digital Workplace | Active
APP-010 | Vulnerability Scanner | Platform Service | Security | High | Hybrid | Tenable | Security Operations | Active

## Risk Register
Risk Register
Risk Score:Likelihood*Impact ¦ 1–4 = Low ¦ 5–9 = Medium ¦ 10–16 = High ¦ 17–25 = Critical
Risk ID | Application ID | Application ID | Risk Category | Risk Description | Likelihood | Impact | Risk Score | Risk Level | Risk Owner | Mitigation / Recommended Action | Status
RSK-001 | RSK-002 | Finance ERP | Access Management | Excessive user privileges may allow unauthorized access to financial data | 3 | 5 | 0 | 0 | Owner - Finance IT | Review user roles and apply least privilege | In Progress
RSK-002 | APP-001 | Finance ERP | Data Protection | Sensitive financial data may be exposed through incorrect access permissions | 3 | 5 | 0 | 0 | Owner - Finance IT | Review data access and permissions | Open
RSK-003 | APP-002 | HR Portal | Access Management | Missing or weak MFA could allow unauthorized employee account access | 4 | 5 | 0 | 0 | Owner - HR IT | Enforce MFA for privileged and user accounts | In Progress
RSK-004 | APP-002 | HR Portal | Data Protection | Personal employee information could be exposed through excessive access | 3 | 5 | 0 | 0 | Owner - HR IT | Conduct access review and restrict sensitive data access | Open
RSK-005 | APP-003 | Customer API Gateway | Vulnerability Management | Unpatched API components may expose services to known vulnerabilities | 3 | 5 | 0 | 0 | Platform Team | Perform regular vulnerability scanning and patching | Open
RSK-006 | APP-003 | Customer API Gateway | Access Management | Weak API authentication could allow unauthorized API requests | 3 | 5 | 0 | 0 | Platform Team | Strengthen authentication and API access controls | In Progress
RSK-007 | APP-004 | Manufacturing MES | Availability | System outage could interrupt manufacturing operations | 3 | 5 | 0 | 0 | OT Applications | Test backups and maintain recovery procedures | Open
RSK-008 | APP-004 | Manufacturing MES | Vulnerability Management | Outdated software components may contain exploitable vulnerabilities | 3 | 5 | 0 | 0 | OT Applications | Maintain patch assessment and vulnerability tracking | In Progress
RSK-009 | APP-005 | Supplier Portal | Access Management | Compromised supplier accounts could provide unauthorized portal access | 3 | 4 | 0 | 0 | Procurement IT | Implement MFA and periodic account reviews | Open
RSK-010 | APP-005 | Supplier Portal | Vulnerability Management | Web application vulnerabilities could expose supplier information | 3 | 4 | 0 | 0 | Procurement IT | Perform periodic vulnerability and security testing | Open
RSK-011 | APP-006 | Data Lake Platform | Data Protection | Incorrect permissions could expose sensitive business data | 3 | 5 | 0 | 0 | Data Platform | Review access permissions and data classification | In Progress
RSK-012 | APP-006 | Data Lake Platform | Cloud Security | Misconfigured cloud storage could result in unauthorized data exposure | 3 | 5 | 0 | 0 | Data Platform | Review cloud configuration and access policies | Open
RSK-013 | APP-007 | Identity Service | Access Management | Compromised identity accounts could provide access to multiple business systems | 4 | 5 | 0 | 0 | IAM Team | Enforce MFA, privileged access controls and monitoring | In Progress
RSK-014 | APP-007 | Identity Service | Availability | Identity service outage could prevent users from accessing critical applications | 3 | 5 | 0 | 0 | IAM Team | Maintain redundancy and recovery procedures | Open
RSK-015 | APP-008 | ITSM Platform | Access Management | Excessive ITSM privileges could allow unauthorized changes to tickets or configurations | 3 | 4 | 0 | 0 | IT Operations | Review roles and apply least privilege | Open
RSK-016 | APP-008 | ITSM Platform | Security Governance | Security evidence and ticket information may not be consistently maintained | 2 | 4 | 0 | 0 | IT Operations | Define documentation and evidence requirements | In Progress
RSK-017 | APP-009 | Corporate Collaboration | Data Protection | Sensitive company information could be shared with unauthorized users | 3 | 4 | 0 | 0 | Digital Workplace | Review sharing permissions and external access | Open
RSK-018 | APP-009 | Corporate Collaboration | Access Management | Compromised user accounts could provide access to corporate information | 3 | 4 | 0 | 0 | Digital Workplace | Enforce MFA and monitor suspicious sign-ins | In Progress
RSK-019 | APP-010 | Vulnerability Scanner | Availability | Scanner service failure could reduce vulnerability monitoring coverage | 2 | 4 | 0 | 0 | Security Operations | Monitor scanner availability and maintain backup processes | Open
RSK-020 | APP-010 | Vulnerability Scanner | Security Governance | Vulnerability results may not be assigned and remediated within defined timelines | 3 | 4 | 0 | 0 | Security Operations | Define ownership, SLA and remediation tracking | In Progress

## Findings
Security Findings
Finding ID | Risk ID | Application | Finding Category | Finding Description | Severity | Source | Owner | Status
FIND-001 | RSK-001 | Finance ERP | Access Management | Excessive user privileges identified | High | Access Review | Finance IT | Open
FIND-002 | RSK-002 | Finance ERP | Data Protection | Sensitive financial data access requires review | High | Security Assessment | Finance IT | Open
FIND-003 | RSK-003 | HR Portal | Authentication | MFA enforcement requires improvement | Critical | Security Assessment | HR IT | In Progress
FIND-004 | RSK-004 | HR Portal | Data Protection | Excessive access to employee information | High | Access Review | HR IT | Open
FIND-005 | RSK-005 | Customer API Gateway | Vulnerability | Unpatched API components identified | High | Vulnerability Scan | Platform Team | Open
FIND-006 | RSK-006 | Customer API Gateway | Authentication | API authentication controls require improvement | High | Security Assessment | Platform Team | In Progress
FIND-007 | RSK-007 | Manufacturing MES | Availability | Recovery testing requires improvement | High | IT/OT Assessment | OT Applications | Open
FIND-008 | RSK-008 | Manufacturing MES | Vulnerability | Outdated software components identified | High | Vulnerability Scan | OT Applications | In Progress
FIND-009 | RSK-009 | Supplier Portal | Access Management | Supplier account access requires periodic review | High | Access Review | Procurement IT | Open
FIND-010 | RSK-010 | Supplier Portal | Web Security | Web application vulnerabilities require remediation | High | Security Testing | Procurement IT | Open

## Remediation
Remediation Tracker
Action ID | Finding ID | Application | Remediation Action | Owner | Priority | Target Date | Status | Evidence | Comments
ACT-001 | FIND-001 | Finance ERP | Review user roles and remove unnecessary privileges | Finance IT | High | 30.09.2026 | In Progress | Access Review | Pending review
ACT-002 | FIND-002 | Finance ERP | Review permissions for sensitive financial data | Finance IT | High | 05.10.2026 | Open | Access Matrix | -
ACT-003 | FIND-003 | HR Portal | Enforce MFA for all users | HR IT | Critical | 25.09.2026 | In Progress | MFA Report | -
ACT-004 | FIND-004 | HR Portal | Restrict access to employee information | HR IT | High | 10.10.2026 | Open | Access Review | -
ACT-005 | FIND-005 | Customer API Gateway | Patch vulnerable API components | Platform Team | High | 01.10.2026 | Open | Scan Report | -

## Assesment
Security Assessment Tracker
Assessment ID | Application | Assessment Type | Assessment Date | Assessor | Findings | Critical Findings | High Findings | Status | Next Review
ASMT-001 | Finance ERP | Application Security Assessment | 15.03.2026 | Security Team | 2 | 0 | 2 | Completed | 15.09.2026
ASMT-002 | HR Portal | Access Security Assessment | 18.04.2026 | Security Team | 2 | 1 | 1 | In Progress | 18.10.2026
ASMT-003 | Customer API Gateway | Vulnerability Assessment | 20.05.2026 | Security Team | 2 | 0 | 2 | Completed | 20.09.2026
ASMT-004 | Manufacturing MES | IT/OT Security Assessment | 22.05.2026 | Security Team | 2 | 0 | 2 | In Progress | 22.10.2026
ASMT-005 | Supplier Portal | Web Security Assessment | 25.05.2026 | Security Team | 2 | 0 | 2 | Planned | 25.11.2026

## Compliance
ISO 27001 Compliance Tracker
Control ID | Security Area | Requirement | Application | Status | Evidence Required | Evidence Required | Owner | Gap/Action
ISO-001 | Access Control | User access should be appropriately managed | Finance ERP | Partially Compliant | Access Review | Access Review | Finance IT | Review privileged accounts
ISO-002 | Authentication | Strong authentication should be implemented | HR Portal | Non-Compliant | MFA Report | MFA Report | HR IT | Implement MFA
ISO-003 | Vulnerability Management | Vulnerabilities should be identified and managed | API Gateway | Partially Compliant | Vulnerability Scan | Vulnerability Scan | Platform Team | Patch open findings
ISO-004 | Backup & Recovery | Critical systems should have recovery procedures | Manufacturing MES | Partially Compliant | Recovery Test | Recovery Test | OT Applications | Perform recovery test
ISO-005 | Data Protection | Sensitive information should have appropriate access controls | Data Lake | Partially Compliant | Access Matrix | Access Matrix | Data Platform | Review permissions
ISO-006 | Logging & Monitoring | Security-relevant activities should be monitored | Identity Service | Compliant | Monitoring Report | Monitoring Report | IAM Team | -
ISO-007 | Incident Management | Security incidents should be recorded and managed | ITSM Platform | Compliant | Incident Records | Incident Records | IT Operations | -
ISO-008 | Security Documentation | Security processes should be documented | ITSM Platform | Partially Compliant | Process Document | Process Document | IT Operations | Update documentation

## KPI Report
Security KPI Report
| KPI | Value | Target | Status
| Total Applications | 0 | 10 | On Track
| Total Risks | 0 | ≤20 | On Track
| Critical Risks | 0 | 0 | Attention
| High Risks | 0 | ≤5 | Attention
| Open Findings | 0 | ≤5 | Attention
| Findings In Progress | 0 | - | On Track
| Remediation Actions Open | 0 | ≤5 | On Track
| Compliance Rate | - | -

## Dashboard
IT APPLICATION SECURITY GOVERNANCE DASHBOARD
Application | Risks | Critical
0 | 0 | 0
RISK DISTRIBUTION |  |  | Compliance Chart
| Critical | 0 |  | Compliant | 0
| High | 0 |  | Partially Compliant | 0
| Medium | 0 |  | Non-Compliant | 0
| Low | 0
Remediation Progress |  |  | Findings
| Open | 0 | Open | 0
| In Progress | 0 | In Progress | 0
| Completed | 0 | Closed | 0